## Timelines
No | Term | Task |  | Status | Assigned To | Start Date | End Date | Duration (Days) | Complete(%) | Depedencies | Notes
1 | Phase 1 | Web Application
2
3 |  | Requirements Analyst
4 |  |  | Define Business Objectives and Goals | Completed | Edwin | 2023-08-28 | 2023-08-28 | 1 | 100%
5 |  |  | Formalize Project Requirements | Completed | Edwin | 2023-08-29 | 2023-08-29 | 2 | 100%
6 |  |  | Define Priorities | Completed | Edwin | 2023-08-30 | 2023-08-30 | 1 | 100%
7 |  |  | Define Project Restrains / Bottleneck | Completed | Edwin | 2023-08-31 | 2023-08-31 | 1 | 100%
8
9 |  | Design
10 |  |  | Research | Completed | Edwin | 2023-08-29 | 2023-08-29 | 1 | 100%
11 |  |  | Proof of Concept | Completed | Edwin | 2023-08-30 | 2023-08-30 | 1 | 100%
12 |  |  | Prototyping | Not Completed | Edwin | 2023-08-30 | 2023-08-31 | 2 | 50% |  | ReactJS for FE / BE
13
14 |  | Development
15 |  |  | ReactJS Web for FE | Not Started | Edwin | 2023-09-04 | 2023-09-22 | 17 | 0%
16 |  |  | ReactJS Web for BE | Not Started | Edwin | 2023-09-18 | 2023-09-29 | 10 | 0%
17 |  |  | Core / Game Api | Not Completed | Cyroch | 2023-09-04 | 2023-09-30 |  | 90% |  | from Backlog earlier
18 |  |  | Client Api | Not Completed | Astan | 2023-09-04 | 2023-09-30 |  | 80% |  | from Backlog earlier
|  |  | Database Migration | Not Completed | Astan/Cyroch | 2023-09-04 | 2023-09-30 |  | 80% |  | from Backlog earlier
19 |  |  | Testing | Not Started |  | 2023-10-28 | 2023-10-28 |  | 0%
20 |  |  | Demo | Not Started |  | 2023-10-29 | 2023-10-29 |  | 0%
21 |  |  | Implementation | Not Started |  | 2023-09-30 | 2023-09-30 |  | 0%
22
23 |  | Quality Assurance
24 |  |  | Reviewing Requirements | Not Started |  | 2023-10-29 | 2023-10-29 | 1 | 0%
25 |  |  | Assuring Quality | Not Started |  | 2023-10-29 | 2023-10-29 | 1 | 0%
26 |  |  | Test Case Creation | Not Started |  | 2023-10-29 | 2023-10-29 | 1 | 0%
27 |  |  | Testing | Not Started |  | 2023-09-30 | 2023-09-30 | 1 | 0%
28
29 |  | Delivery & Support
30 |  |  | Showcase | Not Started |  | 2023-09-30 | 2023-09-30 | 1 | 0%
31 |  |  | Launch | Not Started |  | 2023-10-01 | 2023-10-01 | 1 | 0%
32 |  |  | Support Plan Creation | Not Started |  | 2023-10-01 | 2023-10-02 | 2 | 0%
33 |  |  | Support Plan Implementation | Not Started |  | 2023-10-03 | 2023-10-30 | 27 | 0%
34
35 | Phase 2 | Mobile Application
36 |  |  | Api Integration | Not Started |  | 2023-10-09 | 2023-10-30 | 23 | 0%

## Priorities
No | Items | Priority | Notes
1 | Reactjs Web / Front End | 1 | 0% Completed
2 | ReactJs / Backend (Admin) | 2 | 0% Completed
3 | Core Api (Python) | 3 | 90 % Completed
4 | Client Api (ExpressJs) | 4 | 80 % Completed
5 | Deployment | 5 | 0% Completed
6 | Development Server | 6 | 0% Completed
7 | Production Server | 7 | 0% Completed
8 | ReactNative for Mobile Apps | 8 | 0% Completed

## Stack
No | Items | Notes
1 | Reactjs for Web
2 | Reat Native for Mobile
3 | ExpressJs
4 | Python / Flask
5 | Game's Provider Api
6 | MySQL
7 | Digital Ocean (Server)

## Restrains
No | Items | Notes
1 | Legality
2 | Production Server
3
4
5
6